Breast Cancer Stage Classification with miRNA

Work Breakdown Structure (WBS)

Project Members - Group #44

Joshua Adegboyo: jadegboyo2023@fau.edu

Anika Baro Villa: abarovilla2021@fau.edu

Nicholas Campos: ncampos2022@fau.edu

Brehon Parker: bparker2012@fau.edu

Advisors

Dr. Ali Ibrahim: aibrahim2014@fau.edu

Dr. Hanqi Zhuang: zhuang@fau.edu

Engineering Design 2 | Fall 2025

# Work Breakdown Structure (WBS)

| WBS Code | Task Name | Description | Responsible Party | Start Date | Duration | Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| 1.0 | Project Initialization | Prepare team, agree on communication channels, share initial documents, align roles and deliverables | All Members | 7/07/2025 | 4 weeks | None |
| 1.1 | Setup Planner & Tools | Set up Teams Planner board, assign roles, create shared folders | All Members | 7/07/2025 | 3 days | None |
| 1.2 | Review Research | Review past research and relevant miRNA papers | All Members | 7/07/2025 | 1 week | None |
| 1.3 | Requirement Gathering & Finalization | Refine functional and non-functional requirements | All Members | 7/07/2025 | 1 week | 1.2 |
| 1.4 | UML and System Design Review | Finalize system design and architecture (class diagrams, data flow) | Nicholas, Anika | 7/10/2025 | 4 days | 1.3 |
| 1.5 | Main Project Summary | Draft a summary of the main project idea | Joshua, Anika | 7/14/2025 | 2 days | 1.3 |
| 1.6 | WBS Creation & Teams Planner Setup | Prepare full project WBS for Canvas; finalize Planner task input | Brehon, Anika | 7/14/2025 | 4 days | 1.4 |
| 1.7 | Project Proposal & Subsystem Demo | Present the proposal and subsystem demo to faculty | All Members | 7/21/2025 | 1 week | 1.2, 1.3, 1.4, 1.6 |
| 1.8 | ED1 Wrap-Up and Semester Reflection | Final check-in, submit documentation, prepare for next phase | All Members | 7/24/2025 | 2 days | 1.6 |
| M1 | Project Initialization Completed | Planning, setup, and initial research review are finished | All Members | 7/30/2025 | - | 1.8 |
| 2.0 | Project Reboot | Regroup, review lessons learned, update plans, and agree on team meeting times | All Members | 8/16/2025 | 5 days | 1.7 |
| 3.0 | Data Preparation | Acquire, clean, and prepare TCGA breast cancer miRNA expression and clinical data for modeling | All Members (led by Dr. Ali) | 8/25/2025 | 5 weeks | 2.0 |
| 3.1 | Download Data (miRNA + Clinical) | Download breast cancer miRNA expression data (TXT format) and corresponding clinical metadata (JSON) from TCGA. Use Cart and Manifest for dataset tracking and reproducibility | All Members | 8/25/2025 | 1 day | 2.0 |
| 3.2 | Data Cleaning | Clean miRNA expression files by checking integrity, handling missing values, removing outliers, and normalizing values (e.g., log₂(x+1)); ensure consistent formats and sample IDs before merging with metadata | All Members | 9/01/2025 | 1 week | 3.1 |
| 3.3 | Data Labeling | Link cleaned miRNA expression data with clinical metadata by case IDs to assign correct breast cancer stage labels (I–IV) | All Members | 9/01/2025 | 1 week | 3.2 |
| 3.4 | Feature Selection | Apply feature selection methods (Chi-Squared, NCA, L1 regularization, and deep learning feature extraction) to identify the most informative miRNAs for stage classification | All Members | 9/08/2025 | 3 weeks | 3.3 |
| M2 | Data Prepared and Cleaned | Clinical and miRNA-seq data have been downloaded, preprocessed, and feature selection completed | All Members | 9/28/2025 | - | 3.4 |
| 4.0 | Model Development | Develop, train, and evaluate ML and DL models | All Members | 9/29/2025 | 5-6 weeks | 3.4 |
| 4.1 | Baseline ML Model Development | Build baseline ML models (SVM, RF) using selected miRNAs; record accuracy, precision, recall, F1-score | Nicholas, Joshua | 9/29/2025 | 1 week | 3.4 |
| 4.2 | Deep Learning Model Development | Develop and train MLP, CNN for comparison; monitor learning curves | Anika, Brehon | 10/06/2025 | 1 week | 4.1 |
| 4.3 | Hyperparameter Tuning | Grid/random search for C, k, LR, l1_ratio | Joshua, Nicholas | 10/13/2025 | 1 week | 4.2 |
| 4.4 | Model Evaluation | Compare ML vs. DL performance using cross-validation, ROC-AUC, precision-recall, confidence intervals | Anika, Brehon | 10/20/2025 | 1 week | 4.3 |
| 4.5 | Error Analysis & Refinement | Analyze misclassifications, tweak parameters, improve model robustness | Nicholas, Brehon | 10/27/2025 | 3 days | 4.4 |
| 4.6 | Interpretation of miRNA Role | Investigate important miRNAs identified and cross-reference with literature | Anika, Joshua | 10/30/2025 | 1 week | 4.5 |
| 4.7 | Explore Generalization & Other Diseases | Optional: Explore additional datasets or disease links | Brehon, Nicholas | 11/03/2025 | 1 week | 4.6 |
| M3 | Core Models Developed and Evaluated | All ML/DL models have been trained, tuned, evaluated, and refined; miRNA roles interpreted | All Members | 11/09/2025 | - | 4.7 |
| 5.0 | Explainability & Visualization | Generate interpretability reports and visualizations | Joshua, Anika | 11/03/2025 | 3 weeks | 4.5 |
| 5.1 | SHAP/LIME Computation | Compute feature-attribution values (SHAP, LIME) | Joshua, Anika | 11/03/2025 | 1.5 weeks | 4.5 |
| 5.2 | Dashboard Development | Build Plotly/Matplotlib dashboards for model insights | Joshua, Anika | 11/10/2025 | 1.5 weeks | 4.5 |
| M4 | Dashboard and Visual Tools Completed | SHAP/LIME analysis and interactive dashboard development completed | Joshua, Anika | 11/23/2025 | - | 5.2 |
| 6.0 | Interface Development & Deployment | Build, test, and deploy web application | All Members | 11/03/2025 | 4 weeks | 4.5 |
| 6.1 | UI/UX Prototyping | Design React wireframes, prototype dashboard | Joshua, Anika | 11/03/2025 | 3 weeks | 4.5 |
| 6.2 | API & Backend | Develop Flask REST API, containerize, deploy | Nicholas, Joshua | 11/03/2025 | 3 weeks | 4.5 |
| 6.3 | Frontend Integration & Testing | Connect React UI to API; run end-to-end tests | Anika, Brehon | 11/17/2025 | 1 week | 6.2 |
| 6.4 | Deployment Optimization | Load testing, security checks, performance tuning | Joshua, Nicholas | 11/24/2025 | 1 week | 6.3 |
| M5 | Web App Fully Developed | UI, backend, and integration complete. Web app is deployed and functional | All Members | 11/30/2025 | - | 6.4 |
| 7.0 | Final Reporting & Close-out | Final validation, paper writing, presentation prep, and submission | All Members | 11/24/2025 | 2 weeks | 6.2 |
| 7.1 | System Validation & User Testing | Run test cases, collect feedback, fix critical issues | Nicholas, Anika | 11/24/2025 | 1 week | 6.2 |
| 7.2 | Final Report Drafting | Write main report, describe methods, results, interpretation, lessons | All Members | 11/24/2025 | 1 week | 6.2 |
| 7.3 | Final Presentation Preparation | Build slide deck, rehearse delivery | All Members | 11/24/2025 | 5 days | 6.2 |
| 7.4 | Final Deliverables Submission | Submit report, code, presentation | All Members | 12/03/2025 | 5 days | 7.3 |
| 7.5 | Project Reflection & Lessons Learned | Document reflections, unexpected issues, suggestions | All Members | 12/03/2025 | 5 days | 7.4 |
| M6 | Final Deliverables Submitted | Final system validated, report and presentation delivered, and reflection documented | All Members | 12/07/2025 | - | 7.5 |